## Defects
Sl No | Submitted By | Submitted Date | Description | Defected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Priyank | Yes | Weights exceeding 50% | Sprint 2 | Mentor | Standards | Applied 50% cap | 2025-09-03 | Closed | Portfolio rules corrected
2 | Priyank | Yes | Plotted graphs for all portfolios instead of one vs individual returns | Sprint 2 | Mentor | Logical | Corrected to single portfolio vs asset | 2025-09-10 | Closed | Visualization aligned with mentor feedback
3 | Priyank | Yes | Model accuracy issue (missing linear dependency) | Sprint 3 | Mentor | Standards | Plan to add linear dependency | 2025-09-25 | Closed | Trained with features that establish linear dependency

## Sheet2
Logical
User Interface
Maintainability
Standards
Others