## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 | 1 | US1 | Choose the data file with at least 2 crypto currencies (either web scrape csv file or download to use as csv) | MUST HAVE | — | Priyank | 3- Completed
1 | 1 | US2 | Store the data in the database | SHOULD HAVE | — | Priyank | 3- Completed
1 | 1 | US3 | Calculate the metrics for the data and store in the data frame | MUST HAVE | — | Priyank | 3- Completed
1 | 1 | US4 | Apply parallel tasks concepts to the above steps | SHOULD HAVE | — | Priyank | 3- Completed
2 | 2 | US5 | Assign weights for the portfolio. Check if weights are assigned based on the rule.(mentioned in 1st september slide) Calculate portfolio return and portfolio risk | MUST HAVE | 1 | Priyank | 3- Completed
2 | 2 | US6 | Create two tables for portfolio and portfolio_assets to store currencies, weights,, returns, risk, metrics Store and Fetch the data | SHOULD HAVE | 1 | Priyank | 3- Completed
2 | 2 | US7 | Parallel Execution - Extend logic: run multiple rule tests in parallel (ThreadPool). Example: run equal-weight, risk-based, performance-based at same time.Save outputs into DB | SHOULD HAVE | — | Priyank | 3- Completed
2 | 2 | US8 | Compare portfolio return vs. single asset return with some sample data Plot the graphs, Draw some insights.Export to csv | MUST HAVE | 1 | Priyank | 3- Completed
2 | 2 | US9 | Prepare a .md file which should contain the milestone 2 work that you have done so far | SHOULD HAVE | — | Priyank | 3- Completed
3 | 3 | US10 | Implement 6 rules to identify risk (in sep 13th slide) Store them in the database .Send email alert if anyone rules fails | MUST HAVE | 1 | Priyank | 3- Completed
3 | 3 | US11 | Predict both portfolio and individual returns using linear regression model | MUST HAVE | 2 | Priyank | 3- Completed
4 | 4 | US12 | Implement rule setter (anyone from Sep 30 slide) and calculate portfolio returns, store in Database | MUST HAVE | 1 | Priyank | 3- Completed
4 | 4 | US13 | Apply stress test and see how portfolio returns behave | MUST HAVE | 4 | Priyank | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 33 | 26 | 6 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US1 | 1 | Collect/download crypto data (BTC, ETH) as CSV | 2025-08-18 | 2025-08-18 | Priyank | Build | 3- Completed | 1 | bar: Day 1
US2 | 2 | Store CSV into SQLite DB (btc_prices, eth_prices) | 2025-08-19 | 2025-08-19 | Priyank | Coding | 3- Completed | 1 | bar: Day 1
US3 | 3 | Implement metrics functions (percent change, moving avg, volatility, signals) | 2025-08-22 | 2025-08-23 | Priyank | Coding | 3- Completed | 2 | bar: Day 1 to Day 2
US3 | 4 | Store metrics into DB (crypto_metrics) | 2025-08-25 | 2025-08-25 | Priyank | Coding | 3- Completed | 2 | Day 1: 2
US3 | 5 | Validate stored metrics with test cases | 2025-08-26 | 2025-08-26 | Priyank | Coding | 3- Completed | 1 | bar: Day 1
US4 | 6 | Implement parallel execution (ThreadPoolExecutor) | 2025-08-27 | 2025-08-27 | Priyank | Unit Test | 3- Completed | 1 | bar: Day 1
SPRINT 2 BACKLOG
US5 | 1 | Assign weights for the portfolio. Check if weights are assigned based on the rule | 2025-09-02 | 2025-09-02 | Priyank | Coding | 3- Completed | 1 | bar: Day 1
US5 | 2 | Calculate portfolio return and portfolio risk | 2025-09-03 | 2025-09-04 | Priyank | Coding | 3- Completed | 2 | bar: Day 1 to Day 2
US6 | 3 | Store portfolio data (weights, return, risk) in database | 2025-09-05 | 2025-09-05 | Priyank | Coding | 3- Completed | 1 | bar: Day 1
US7 | 4 | For different weight rules assigned to Portfolio ,implement parallel execution | 2025-09-06 | 2025-09-06 | Priyank | Coding | 3- Completed | 1 | bar: Day 1
US8 | 5 | Compare portfolio return vs individual assets | 2025-09-08 | 2025-09-09 | Priyank | Coding | 3- Completed | 2 | bar: Day 1 to Day 2
US8 | 6 | Plot portfolio vs assets and draw insights | 2025-09-10 | 2025-09-10 | Priyank | Coding | 3- Completed | 2 | Day 1: 2
SPRINT 3 BACKLOG
US10 | 1 | Implement 6 risk rules in Risk_checker.py | 2025-09-16 | 2025-09-17 | Priyank | Coding | 3- Completed | 2 | bar: Day 1 to Day 2
US10 | 2 | Store risk rule results into DB | 2025-09-18 | 2025-09-18 | Priyank | Coding | 3- Completed | 1 | bar: Day 1
US10 | 3 | Implement email alerts when any rule fails | 2025-09-19 | 2025-09-19 | Priyank | Coding | 3- Completed | 1 | bar: Day 1
US11 | 4 | Implement linear regression model in Predictor.py for portfolio + assets | 2025-09-22 | 2025-09-25 | Priyank | Coding | 2- In Progress | 4 | Day 1: 2; Day 2: 1; Day 3: 1
US11 | 5 | Validate predictions (R², RMSE, accuracy check) | 2025-09-26 | 2025-09-26 | Priyank | Unit Test | 2- In Progress | 1 | bar: Day 1
SPRINT 4 BACKLOG
US12 | 1 | Implement any one Invesstment spreading rule other than equal weight rule | 2025-09-30 | 2025-09-01 | Priyank | Coding | 3- Completed | 3 | Day 1: 2; Day 2: 1
US12 | 2 | calculate the portfolio return from the weight assigned using the rule and store it | 2025-09-01 | 2025-09-01 | Priyank | Coding | 3- Completed | 1 | bar: Day 1
US13 | 3 | Apply stress test to see how portfolio behaves in different market scenarios | 2025-09-02 | 2025-09-02 | Priyank | Coding | 3- Completed | 2 | Day 1: 2
US13 | 4 | Analyze the insight from the stress test | 2025-09-03 | 2025-09-03 | Priyank | Others | 3- Completed | 1 | bar: Day 1
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
1 | 13th Aug | Understanding the project and guidelines to take care of along with date time module | Read from the slides about guidelines and implemented datetime module
1 | 14th Aug | Milestone 1 discussion along with SQLite understanding | SQLite implemented with CRUD commands
1 | 18th Aug | Crypto terminologies and raw csv handling of chosen asset to track | Understood crypto terminologies from slides and chose BTC to track
1 | 19th Aug | CSV handling with pandas | Pandas implemented in code editor
1 | 20th Aug | Parallel tasking using concurrent.futures | Learned and implemented parallel tasking using thread pool
1 | 21st Aug | Understanding the numPy | Performed various numPy operations
1 | 22nd Aug | Different Math calculation like percent_change ,volatility on the asset | Applied different math operations for the crypto asset like volatility and percent change
1 | 25th Aug | Storing the metrics in DB | Stored the math operations values(metrics) in DB
1 | 28th Aug | Sprint evaluation | feedback taken and improved
1 | 29th Aug | sprint evaluation | —
1 | 30th Aug | Introduction to milestone 2 | —
2 | 1st Sep | Learning about different weight allocation rule | Implemented 3 weight rule from 5
2 | 2nd Sep | Apply weight rule and calculate portfolio return and risk and store it in db | 3 weight rules applied on data stored in DB and portfolio return and risk calculated
2 | 3rd Sep | Continue with the task on Sep, 2nd | Improved the selection of 3 rules and again did the calculation
2 | 4th Sep | Apply parallel execution to calculate different weight rule at same time | Applied paralled execution to calculate weights using the rules for each at same time
2 | 8th Sep | Compare the portfolio return vs single asset return and plot the graph for it | compared and plotted a line graph for portfolio vs all 3 asset for all data
2 | 9th Sep | Sprint evaluation and Create a .md file which contains the documentation about milestone 2 | feedback taken and improved on graph with plotting only 15 days to show clear insights
2 | 10th Sep | Sprint evaluation | contiued with improvement and creation of .md file
2 | 12th Sep | Sprint evaluation | —
3 | 15th Sep | Understanding about how to send email alerts | Implemented the email sending using SMTP server
3 | 16th Sep | Different Risk rule discussion | learned about 6 risks
3 | 17th Sep | continue with the task on Sep, 15th | Implemented sharpe and beta rule with advised threshold
3 | 18th Seo | Predict both portfolio and individual return using linear regression model | Linear regression implemented with feature selection having linear depenedency with assets
3 | 20th Sep | Agile documentation explained | went through all the documents provided by mentor
3 | 23rd Sep | Sprint evaluation | advised on model accuracy
3 | 24th Sep | Sprint evaluation | model accuracy imporved
3 | 26th Sep | Sprint evaluation | —
4 | 30th Sep | Understanding investment spreading rules | implemented one rule ( sharpe maximization rule ) for weight allocation
4 | 1st Oct | Understanding how to apply stress test and check how portfolio behaves | applied stress test for sample data and checked whether the portfolio behaves with the market or not
4 | 3rd Oct | Sprint evaluation | Little change in stress test to simulate better
4 | 4th Oct | Sprint evaluation | —
4 | 6th Oct | Mock Presentation | Better the presentation by explaining the project and not to go deep with the terminologies

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-08-13 | 2025-08-29 | Priyank | Use minimum 2 assets | — | Metric calculation aligned | Clarified with mentor; implemented with minimum 2 assets
2 | Sprint 1 | 2025-08-13 | 2025-08-29 | Priyank | Review metric calculation logic | — | Continue with current calculation methods | Reviewed metric calculation and aligned with mentor feedback
3 | Sprint 2 | 2025-09-01 | 2025-09-12 | Priyank | Use 3 assets for portfolio return weights | — | Continue portfolio optimization | Implemented as advised
4 | Sprint 2 | 2025-09-01 | 2025-09-12 | Priyank | Apply weight capping rules | Unclear rules previously | Continue using weight rules | Clarified with mentor; capped weights at 50%
5 | Sprint 2 | 2025-09-01 | 2025-09-12 | Priyank | Plot one portfolio return vs asset | Multiple plots | Continue plotting portfolio returns | Implemented as advised
6 | Sprint 3 | 2025-09-15 | 2025-09-26 | Priyank | Build linear dependency for regression model | Missing linear dependency | Continue performance improvement | Checked which features have linear dependency in predicting the returns
7 | Sprint 3 | 2025-09-15 | 2025-09-26 | Priyank | Improve Features that align with prediction for individual assets | Features that don't contribute in prediction | Portfolio returns and USDC values predicted well | Used KBest feature selection and standard scalar
8 | Sprint 4 | 2025-09-30 | 2025-10-04 | Priyank | Use Any Investment spreading rule | Equal weight rule | Any other rule | Checked in the slides for 30th sept to implement other rule
9 | Sprint 4 | 2025-09-30 | 2025-10-04 | Priyank | Apply stress test | — | Simulate the portfolio return in different scenarios of market | Tested the portfolio return for weight using rule on sampled data for different scenarios of market